## UAC
Sprint # | Module | Feature / Function | User Story | Acceptance Criteria | I | N | V | E | S | T | INVEST Notes (if any FALSE)
1 | Authentication & Access | Login | As a system user, I want to login using my verified credentials, in order to securely access the system | 1) Given valid credentials, when submitted, then the user is authenticated and redirected to their role-specific dashboard. 2) Given invalid credentials, when submitted, then the system shows an error and denies access. 3) Given 3 consecutive failed attempts, then the account is temporarily locked or warned. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
1 | Authentication & Access | Password Reset | As a system user, I want to reset my password with Admin assistance, so that I can regain access if I forget my credentials | 1) Given a reset request, when Admin resets it, then a new temporary password is issued. 2) Given first login with a temp password, then the user is prompted to set a new one. 3) Only an Admin account can trigger a reset for another user. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
1 | Authentication & Access | Role-Based Access Control | As an Admin, I want each role (Operator, Cashier, Appraiser) restricted to their permitted screens, so that staff only access what their job requires | 1) Given a logged-in user with role X, when they attempt a screen outside their permissions, then access is denied/redirected. 2) Given an Admin, then all modules are accessible. 3) Role permissions are configurable by Admin only. | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | Not Independent: requires Login to exist first. Not Small: touches every screen across 4 roles - recommend splitting per role if capacity is tight.
1 | Authentication & Access | Manage User Accounts | As an Admin, I want to create, edit, and deactivate staff accounts with assigned roles, so that only authorized people can access the system | 1) Given valid new account details, when submitted, then a new staff account with the assigned role is created. 2) Given an existing account, when edited, then changes are saved and reflected immediately. 3) Given a deactivated account, then that user can no longer log in. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
1 | Authentication & Access | Session Timeout | As a system user, I want my session to lock after a period of inactivity, so that sensitive data isn't exposed if I step away | 1) Given no activity for X minutes, then the system automatically logs the user out. 2) Given a timed-out session, when the user returns, then they must log in again to continue. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
1 | System Configuration | Configure Business Rules | As an Admin, I want to set the current gold price, interest rate, loan-to-value percentage, and grace period, so that appraisals and loans use up-to-date values | 1) Given new values entered, when saved, then updates are stored and immediately available to other modules. 2) Given invalid input (negative/non-numeric), then the system rejects it with an error. 3) Given the app restarts, then saved settings persist. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
2 | Customer Management | Register New Customer | As an Operator, I want to register a new customer with their profile and government ID, so that they can be linked to future loans | 1) Given required fields (name, address, contact, ID) are filled, when submitted, then a new customer record is created. 2) Given a missing required field, then the system blocks submission with a validation message. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
2 | Customer Management | Verify Customer Identity (AML) | As an Operator, I want the system to verify a customer's identity against AML checks, so that the pawnshop doesn't onboard a flagged individual | 1) Given a submitted registration, when AML check runs, then the result (clear/flagged) is recorded against the customer. 2) Given a flagged result, then the system visibly warns the Operator before proceeding. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: requires a customer record (Register New Customer) to exist first.
2 | Customer Management | Update Customer Profile | As an Operator, I want to update an existing customer's profile, so that records stay accurate when information changes | 1) Given an existing customer record, when fields are edited and saved, then the updated data is persisted. 2) Given an edit history requirement, then prior values remain visible in the audit trail. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
2 | Customer Management | View Transaction History | As an Operator, I want to view a customer's past transaction history, so that I can answer their questions or spot repeat patterns | 1) Given a customer with past loans/payments, when their profile is opened, then a chronological transaction list is displayed. 2) Given a customer with no history, then an empty state message is shown instead of an error. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: only meaningful once Loan & Transaction data exists (Sprints 4-5); screen can be scaffolded early but fully tested later.
2 | Customer Management | Check Blacklist Status | As an Operator, I want the system to automatically check a customer's blacklist status before a new loan or appraisal, so that flagged customers are stopped early | 1) Given a blacklisted customer, when a new loan or appraisal is started, then the system blocks the action and displays a warning. 2) Given a non-blacklisted customer, then the transaction proceeds normally. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: requires a customer record and a blacklist flag source to exist first.
3 | Appraisal and Valuation | Record Gold Item Details | As an Appraiser, I want to record a gold item's weight, karat, purity, and condition, so that its value can be calculated accurately | 1) Given weight, karat, purity, and condition are entered, when saved, then an item record is created and linked to the customer. 2) Given an out-of-range value (e.g., negative weight), then the system rejects the entry. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
3 | Appraisal and Valuation | Capture Item Photo and Notes | As an Appraiser, I want to attach photos and notes to an item during appraisal, so that there's a visual record in case of disputes | 1) Given at least one photo is uploaded, when saved, then it is attached to the item record. 2) Given free-text notes are entered, then they are saved alongside the photos. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
3 | Appraisal and Valuation | Calculate Valuation & Loan Range | As an Appraiser, I want the system to auto-calculate a suggested valuation and loan range from current gold price and item details, so that pricing is consistent and fast | 1) Given item details and the live gold price, when calculated, then a valuation and a suggested loan range (using LTV%) are displayed. 2) Given the gold price is missing/unavailable, then the system prompts for manual entry instead of failing silently. | FALSE | TRUE | TRUE | FALSE | TRUE | TRUE | Not Independent: depends on System Configuration (gold price/LTV%) and Record Gold Item Details. Not Estimable: exact valuation formula was never numerically confirmed with the client - effort cannot be reliably sized until that gap is closed.
3 | Appraisal and Valuation | Flag Counterfeit Risk | As the System, I want to flag an item as counterfeit risk when purity results fall outside the expected range, so that suspect items are caught before a loan is issued | 1) Given a purity result outside the expected range for the claimed karat, then the item is automatically flagged and the transaction is paused. 2) Given a flagged item, then an alert is sent to the Admin. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: requires the valuation/purity calculation to exist first.
3 | Appraisal and Valuation | Resolve Counterfeit Flag | As an Admin, I want to review and clear items flagged as counterfeit risk, so that legitimate transactions aren't permanently blocked by a false positive | 1) Given a flagged item, when Admin reviews and clears it, then the transaction is unblocked and the resolution is logged. 2) Given Admin confirms the risk instead, then the transaction is permanently stopped and logged. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: requires Flag Counterfeit Risk to exist first.
4 | Loan and Transaction Management | Create Pawn Loan & Issue Ticket | As a Cashier, I want to create a pawn loan and issue a printed pawn ticket, so that the customer has verifiable proof of the transaction | 1) Given a verified customer and an appraised, unflagged item, when the loan is created, then a loan record is generated and a pawn ticket is printed (or PDF fallback). 2) Given loan creation succeeds, then a matching inventory record and initial cash flow entry are created automatically. | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | Not Independent: requires Customer, Appraisal, and blacklist/counterfeit checks to all be complete first. Not Small: combines loan logic, ticket printing hardware, and two downstream triggers (inventory + cash flow) in one story - highest-risk item in the backlog.
4 | Loan and Transaction Management | Record Customer Payment | As a Cashier, I want to record customer payments against an active loan, so that balances stay accurate | 1) Given an active loan, when a payment is recorded, then the remaining balance is recalculated and a receipt is issued. 2) Given a payment amount exceeding the balance, then the system rejects or flags it for review. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: requires Create Pawn Loan to exist first.
4 | Loan and Transaction Management | Process Loan Extension | As a Cashier, I want to process a loan extension with recalculated maturity and additional interest, so that customers can keep their item pawned legitimately | 1) Given an active loan before its grace period expires, when an extension is requested, then a new maturity date and additional interest are calculated and applied. 2) Given an extension is applied, then the loan's extension count is incremented and logged. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: requires Create Pawn Loan to exist first.
5 | Loan and Transaction Management | Redeem Pawned Item | As a Cashier, I want to process full redemption of a pawned item, so that the customer can reclaim their gold once fully paid | 1) Given a loan fully paid, when redemption is processed, then the loan is closed and the item status changes to Redeemed. 2) Given redemption is completed, then the item is released from inventory tracking. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: requires Create Pawn Loan and Record Customer Payment to exist first.
5 | Loan and Transaction Management | Process Loan Default & Forfeiture | As the System, I want to detect when a loan has passed its maturity date and grace period, so that overdue loans are flagged for forfeiture without manual tracking | 1) Given a loan past its maturity date and grace period with no extension or full payment, then the system automatically marks it as defaulted. 2) Given a loan is marked defaulted, then the linked item's status is updated to Forfeited. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: requires Create Pawn Loan and Configure Business Rules (grace period) to exist first.
5 | Loan and Transaction Management | Lost Ticket Alternate Verification | As a Cashier, I want an alternate verification process for a customer who lost their pawn ticket, so that they aren't blocked from paying or redeeming | 1) Given a customer without a physical ticket, when identity is verified through the customer record instead, then the Cashier can proceed with payment or redemption. 2) Given the alternate verification is used, then the event is logged in the audit trail. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: requires Customer Management and Create Pawn Loan to exist first.
6 | Inventory and Collateral Tracking | Register Pawned Item in Inventory | As an Operator, I want newly pawned items automatically registered into inventory with a vault location, so that the vault reflects system records | 1) Given a new loan is created, then an inventory record with an assigned vault location is automatically generated. 2) Given the inventory record exists, then it is linked to both the item and the loan. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: automatically triggered by Create Pawn Loan, so it cannot be tested standalone.
6 | Inventory and Collateral Tracking | Update Item Status | As an Operator, I want item status updated automatically as loans progress, so that inventory always reflects the current state of each item | 1) Given a loan changes state (extended, redeemed, forfeited), then the linked item's inventory status updates automatically to match. 2) Given a status change occurs, then it is timestamped and logged. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: depends on Register Pawned Item in Inventory and the loan lifecycle stories.
6 | Inventory and Collateral Tracking | Perform Physical Inventory Audit | As an Admin, I want to reconcile the physical vault count against system inventory records, so that discrepancies are caught early | 1) Given a physical count is entered, when compared against system records, then any discrepancies are highlighted. 2) Given an audit is completed, then the audit result and timestamp are saved for reference. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: requires inventory records to already exist.
6 | Inventory and Collateral Tracking | Prepare Forfeited Items for Auction | As an Operator, I want to batch forfeited items together for auction preparation, so that unredeemed collateral can be efficiently liquidated | 1) Given one or more items with Forfeited status, when batched, then an auction-prep list is generated. 2) Given an item is added to a batch, then its status reflects it is queued for auction. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: requires forfeited items to exist (depends on Process Loan Default & Forfeiture).
7 | Financial and Accounting | Record Cash Flow Transaction | As the System, I want to automatically record cash flow entries when a loan, payment, or forfeiture occurs, so that the ledger is always current | 1) Given a loan, payment, or forfeiture event occurs, then a corresponding cash flow entry is automatically created. 2) Given the entry is created, then it correctly reflects inflow or outflow direction and amount. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: automatically triggered by Loan & Transaction Management stories, so it cannot be tested standalone.
7 | Financial and Accounting | Track Daily Cash Position | As the System, I want to update the daily cash position automatically, so that Admin always sees an accurate running balance | 1) Given cash flow entries for the day, when viewed, then a running total (cash in vs. cash out) is displayed. 2) Given a new day begins, then the position resets/rolls over correctly. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: depends on Record Cash Flow Transaction.
7 | Financial and Accounting | Record Operating Expenses & Revenue | As an Operator, I want to record non-loan operating expenses and revenue, so that the financial picture is complete | 1) Given an expense or revenue entry with amount and category, when saved, then it appears in the financial records. 2) Given an invalid amount (e.g., zero or negative where not applicable), then the system rejects the entry. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
7 | Financial and Accounting | Generate Financial Ledger Entries | As the System, I want to generate formal financial ledger entries, so that the pawnshop has a proper accounting record | 1) Given cash flow and expense/revenue data for a period, when compiled, then structured ledger entries are generated. 2) Given the ledger is generated, then totals reconcile with the daily cash position. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: depends on Record Cash Flow Transaction and Record Operating Expenses & Revenue.
8 | Compliance and Security | Log System Transaction (Audit Trail) | As the System, I want to log every create, update, and delete action across all modules, so that a complete audit trail exists without manual logging | 1) Given any create, update, or delete action in any module, then an audit entry is recorded with user, timestamp, and change details. 2) Given an audit entry exists, then it is read-only and cannot be edited or deleted by any user, including Admin. | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | Not Independent: to be fully meaningful, it must be retrofitted into every module built in prior sprints, not just new ones. Not Small: this is a cross-cutting concern spanning the whole system - the team flagged in Sprint 1's retrospective that building it in from day one would have been better than retrofitting it late.
8 | Compliance and Security | Flag & Review Suspicious Activity | As an Admin, I want to review system-flagged suspicious activity and decide whether to dismiss, investigate, or blacklist the customer, so that the pawnshop stays AML-compliant | 1) Given a transaction pattern matches AML risk rules, then the system automatically creates a suspicious activity flag. 2) Given a flag exists, when Admin reviews it, then they can select Dismiss, Investigate, or Blacklist, and the decision is logged. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: depends on the Audit Trail and Customer Management stories to have data to evaluate.
8 | Compliance and Security | Send Due-Date Reminder Notification | As the System, I want to send due-date reminders to customers before loan maturity, so that redemption/extension rates improve and defaults are reduced | 1) Given a loan is approaching its maturity date, then a reminder is automatically sent to the customer ahead of time. 2) Given a reminder is sent, then the event is logged for reference. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: depends on Create Pawn Loan for maturity date data.
9 | Reporting and Management Insights | Generate Outstanding Loans Report | As an Admin, I want to generate an Outstanding Loans report, so that I can monitor all currently active loans | 1) Given active loans exist, when the report is generated, then it lists each loan with customer, amount, and due date. 2) Given no active loans exist, then the report shows an empty state rather than an error. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: depends on Loan & Transaction Management data existing.
9 | Reporting and Management Insights | Generate Overdue Loans Report | As an Admin, I want to generate an Overdue Loans report, so that I can follow up on loans past their due date | 1) Given loans past their due date exist, when the report is generated, then it lists each with days overdue. 2) Given filters are applied (date range), then the report updates accordingly. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: depends on Loan & Transaction Management data existing.
9 | Reporting and Management Insights | Generate Inventory Aging Report | As an Admin, I want to generate an Inventory Aging report, so that I can see how long items have sat in the vault | 1) Given inventory records exist, when the report is generated, then it lists each item with days in vault. 2) Given an item exceeds a configurable aging threshold, then it is visually highlighted. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: depends on Inventory and Collateral Tracking data existing.
9 | Reporting and Management Insights | Generate Financial Summary | As an Admin, I want to generate a Financial Summary report, so that I can review revenue and expenses at a glance | 1) Given financial ledger data exists, when the report is generated, then revenue, expenses, and net position are summarized for the selected period. 2) Given a date range is selected, then the summary recalculates for that range. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: depends on Financial and Accounting data existing.
9 | Reporting and Management Insights | Generate Compliance/AML Report | As an Admin, I want to generate a Compliance/AML report, so that I can share it with regulators or auditors | 1) Given AML checks, blacklist actions, and suspicious activity flags exist, when the report is generated, then all are compiled into a single regulator-facing document. 2) Given the report is generated, then it includes the date range and is timestamped for audit purposes. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: depends on Customer Management and Compliance and Security data existing.
9 | Reporting and Management Insights | View Trends & Analytics Dashboard | As an Admin, I want to view a trends and analytics dashboard, so that I can spot patterns without manually reading raw reports | 1) Given historical transaction data exists, when the dashboard is opened, then key trends (volume, redemption rate, forfeiture rate) are visualized. 2) Given a date range filter is applied, then the visualizations update accordingly. | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | Not Independent: depends on all prior reporting data sources. Not Small: aggregates multiple data sources into one dashboard - larger than a typical single story. Not Testable as written: 'spot patterns' is subjective - needs concrete defined metrics/thresholds before it can be objectively verified.
9 | Reporting and Management Insights | Export or Print Reports | As an Admin, I want to export or print any report, so that I can share physical or digital copies with stakeholders | 1) Given any generated report, when Export is selected, then a PDF copy is produced. 2) Given Print is selected, then the report sends correctly to the configured printer. | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | Not Independent: depends on all report-generation stories (34-39) existing first.

## Product Backlog
# | Module | Functionality | User Story | Hours
1 | Authentication & Access | Login | As a system user, I want to login using my verified credentials, in order to securely access the system | 1
2 | Authentication & Access | Password Reset | As a system user, I want to reset my password with Admin assistance, so that I can regain access if I forget my credentials | 0.5
3 | Authentication & Access | Role-Based Access Control | As an Admin, I want each role (Operator, Cashier, Appraiser) restricted to their permitted screens, so that staff only access what their job requires | 1.5
4 | Authentication & Access | Manage User Accounts | As an Admin, I want to create, edit, and deactivate staff accounts with assigned roles, so that only authorized people can access the system | 1
5 | Authentication & Access | Session Timeout | As a system user, I want my session to lock after a period of inactivity, so that sensitive data isn't exposed if I step away | 0.3
6 | System Configuration | Configure Business Rules | As an Admin, I want to set the current gold price, interest rate, loan-to-value percentage, and grace period, so that appraisals and loans use up-to-date values | 1
7 | Customer Management | Register New Customer | As an Operator, I want to register a new customer with their profile and government ID, so that they can be linked to future loans | 1
8 | Customer Management | Verify Customer Identity (AML) | As an Operator, I want the system to verify a customer's identity against AML checks, so that the pawnshop doesn't onboard a flagged individual | 1
9 | Customer Management | Update Customer Profile | As an Operator, I want to update an existing customer's profile, so that records stay accurate when information changes | 0.5
10 | Customer Management | View Transaction History | As an Operator, I want to view a customer's past transaction history, so that I can answer their questions or spot repeat patterns | 0.75
11 | Customer Management | Check Blacklist Status | As an Operator, I want the system to automatically check a customer's blacklist status before a new loan or appraisal, so that flagged customers are stopped early | 0.5
12 | Appraisal and Valuation | Record Gold Item Details | As an Appraiser, I want to record a gold item's weight, karat, purity, and condition, so that its value can be calculated accurately | 1
13 | Appraisal and Valuation | Capture Item Photo and Notes | As an Appraiser, I want to attach photos and notes to an item during appraisal, so that there's a visual record in case of disputes | 0.75
14 | Appraisal and Valuation | Calculate Valuation & Loan Range | As an Appraiser, I want the system to auto-calculate a suggested valuation and loan range from current gold price and item details, so that pricing is consistent and fast | 1.5
15 | Appraisal and Valuation | Flag Counterfeit Risk | As the System, I want to flag an item as counterfeit risk when purity results fall outside the expected range, so that suspect items are caught before a loan is issued | 1
16 | Appraisal and Valuation | Resolve Counterfeit Flag | As an Admin, I want to review and clear items flagged as counterfeit risk, so that legitimate transactions aren't permanently blocked by a false positive | 0.5
17 | Loan and Transaction Management | Create Pawn Loan & Issue Ticket | As a Cashier, I want to create a pawn loan and issue a printed pawn ticket, so that the customer has verifiable proof of the transaction | 2
18 | Loan and Transaction Management | Record Customer Payment | As a Cashier, I want to record customer payments against an active loan, so that balances stay accurate | 1
19 | Loan and Transaction Management | Process Loan Extension | As a Cashier, I want to process a loan extension with recalculated maturity and additional interest, so that customers can keep their item pawned legitimately | 1.5
20 | Loan and Transaction Management | Redeem Pawned Item | As a Cashier, I want to process full redemption of a pawned item, so that the customer can reclaim their gold once fully paid | 1
21 | Loan and Transaction Management | Process Loan Default & Forfeiture | As the System, I want to detect when a loan has passed its maturity date and grace period, so that overdue loans are flagged for forfeiture without manual tracking | 1.5
22 | Loan and Transaction Management | Lost Ticket Alternate Verification | As a Cashier, I want an alternate verification process for a customer who lost their pawn ticket, so that they aren't blocked from paying or redeeming | 1
23 | Inventory and Collateral Tracking | Register Pawned Item in Inventory | As an Operator, I want newly pawned items automatically registered into inventory with a vault location, so that the vault reflects system records | 0.75
24 | Inventory and Collateral Tracking | Update Item Status | As an Operator, I want item status updated automatically as loans progress, so that inventory always reflects the current state of each item | 0.5
25 | Inventory and Collateral Tracking | Perform Physical Inventory Audit | As an Admin, I want to reconcile the physical vault count against system inventory records, so that discrepancies are caught early | 1
26 | Inventory and Collateral Tracking | Prepare Forfeited Items for Auction | As an Operator, I want to batch forfeited items together for auction preparation, so that unredeemed collateral can be efficiently liquidated | 0.75
27 | Financial and Accounting | Record Cash Flow Transaction | As the System, I want to automatically record cash flow entries when a loan, payment, or forfeiture occurs, so that the ledger is always current | 1
28 | Financial and Accounting | Track Daily Cash Position | As the System, I want to update the daily cash position automatically, so that Admin always sees an accurate running balance | 0.75
29 | Financial and Accounting | Record Operating Expenses & Revenue | As an Operator, I want to record non-loan operating expenses and revenue, so that the financial picture is complete | 0.75
30 | Financial and Accounting | Generate Financial Ledger Entries | As the System, I want to generate formal financial ledger entries, so that the pawnshop has a proper accounting record | 1
31 | Compliance and Security | Log System Transaction (Audit Trail) | As the System, I want to log every create, update, and delete action across all modules, so that a complete audit trail exists without manual logging | 1.5
32 | Compliance and Security | Flag & Review Suspicious Activity | As an Admin, I want to review system-flagged suspicious activity and decide whether to dismiss, investigate, or blacklist the customer, so that the pawnshop stays AML-compliant | 1
33 | Compliance and Security | Send Due-Date Reminder Notification | As the System, I want to send due-date reminders to customers before loan maturity, so that redemption/extension rates improve and defaults are reduced | 0.75
34 | Reporting and Management Insights | Generate Outstanding Loans Report | As an Admin, I want to generate an Outstanding Loans report, so that I can monitor all currently active loans | 1
35 | Reporting and Management Insights | Generate Overdue Loans Report | As an Admin, I want to generate an Overdue Loans report, so that I can follow up on loans past their due date | 1
36 | Reporting and Management Insights | Generate Inventory Aging Report | As an Admin, I want to generate an Inventory Aging report, so that I can see how long items have sat in the vault | 1
37 | Reporting and Management Insights | Generate Financial Summary | As an Admin, I want to generate a Financial Summary report, so that I can review revenue and expenses at a glance | 1
38 | Reporting and Management Insights | Generate Compliance/AML Report | As an Admin, I want to generate a Compliance/AML report, so that I can share it with regulators or auditors | 1.5
39 | Reporting and Management Insights | View Trends & Analytics Dashboard | As an Admin, I want to view a trends and analytics dashboard, so that I can spot patterns without manually reading raw reports | 1.5
40 | Reporting and Management Insights | Export or Print Reports | As an Admin, I want to export or print any report, so that I can share physical or digital copies with stakeholders | 0.75

## Sprint Backlog
# | Sprint | PB ID | Module | Functionality | User Story | Date Start | Date End | Assigned | Status
Sprint 1 - Core Setup & Configuration
1 | Sprint 1 | 1 | Authentication & Access | Login | As a system user, I want to login using my verified credentials, in order to securely access the system | TBD | TBD |  | Pending
2 | Sprint 1 | 2 | Authentication & Access | Password Reset | As a system user, I want to reset my password with Admin assistance, so that I can regain access if I forget my credentials | TBD | TBD |  | Pending
3 | Sprint 1 | 3 | Authentication & Access | Role-Based Access Control | As an Admin, I want each role (Operator, Cashier, Appraiser) restricted to their permitted screens, so that staff only access what their job requires | TBD | TBD |  | Pending
4 | Sprint 1 | 4 | Authentication & Access | Manage User Accounts | As an Admin, I want to create, edit, and deactivate staff accounts with assigned roles, so that only authorized people can access the system | TBD | TBD |  | Pending
5 | Sprint 1 | 5 | Authentication & Access | Session Timeout | As a system user, I want my session to lock after a period of inactivity, so that sensitive data isn't exposed if I step away | TBD | TBD |  | Pending
6 | Sprint 1 | 6 | System Configuration | Configure Business Rules | As an Admin, I want to set the current gold price, interest rate, loan-to-value percentage, and grace period, so that appraisals and loans use up-to-date values | TBD | TBD |  | Pending
Sprint 2 - Customer Management
7 | Sprint 2 | 7 | Customer Management | Register New Customer | As an Operator, I want to register a new customer with their profile and government ID, so that they can be linked to future loans | TBD | TBD |  | Pending
8 | Sprint 2 | 8 | Customer Management | Verify Customer Identity (AML) | As an Operator, I want the system to verify a customer's identity against AML checks, so that the pawnshop doesn't onboard a flagged individual | TBD | TBD |  | Pending
9 | Sprint 2 | 9 | Customer Management | Update Customer Profile | As an Operator, I want to update an existing customer's profile, so that records stay accurate when information changes | TBD | TBD |  | Pending
10 | Sprint 2 | 10 | Customer Management | View Transaction History | As an Operator, I want to view a customer's past transaction history, so that I can answer their questions or spot repeat patterns | TBD | TBD |  | Pending
11 | Sprint 2 | 11 | Customer Management | Check Blacklist Status | As an Operator, I want the system to automatically check a customer's blacklist status before a new loan or appraisal, so that flagged customers are stopped early | TBD | TBD |  | Pending
Sprint 3 - Appraisal & Valuation
12 | Sprint 3 | 12 | Appraisal and Valuation | Record Gold Item Details | As an Appraiser, I want to record a gold item's weight, karat, purity, and condition, so that its value can be calculated accurately | TBD | TBD |  | Pending
13 | Sprint 3 | 13 | Appraisal and Valuation | Capture Item Photo and Notes | As an Appraiser, I want to attach photos and notes to an item during appraisal, so that there's a visual record in case of disputes | TBD | TBD |  | Pending
14 | Sprint 3 | 14 | Appraisal and Valuation | Calculate Valuation & Loan Range | As an Appraiser, I want the system to auto-calculate a suggested valuation and loan range from current gold price and item details, so that pricing is consistent and fast | TBD | TBD |  | Pending
15 | Sprint 3 | 15 | Appraisal and Valuation | Flag Counterfeit Risk | As the System, I want to flag an item as counterfeit risk when purity results fall outside the expected range, so that suspect items are caught before a loan is issued | TBD | TBD |  | Pending
16 | Sprint 3 | 16 | Appraisal and Valuation | Resolve Counterfeit Flag | As an Admin, I want to review and clear items flagged as counterfeit risk, so that legitimate transactions aren't permanently blocked by a false positive | TBD | TBD |  | Pending
Sprint 4 - Loan Creation & Payments
17 | Sprint 4 | 17 | Loan and Transaction Management | Create Pawn Loan & Issue Ticket | As a Cashier, I want to create a pawn loan and issue a printed pawn ticket, so that the customer has verifiable proof of the transaction | TBD | TBD |  | Pending
18 | Sprint 4 | 18 | Loan and Transaction Management | Record Customer Payment | As a Cashier, I want to record customer payments against an active loan, so that balances stay accurate | TBD | TBD |  | Pending
19 | Sprint 4 | 19 | Loan and Transaction Management | Process Loan Extension | As a Cashier, I want to process a loan extension with recalculated maturity and additional interest, so that customers can keep their item pawned legitimately | TBD | TBD |  | Pending
Sprint 5 - Loan Creation & Payments
20 | Sprint 5 | 20 | Loan and Transaction Management | Redeem Pawned Item | As a Cashier, I want to process full redemption of a pawned item, so that the customer can reclaim their gold once fully paid | TBD | TBD |  | Pending
21 | Sprint 5 | 21 | Loan and Transaction Management | Process Loan Default & Forfeiture | As the System, I want to detect when a loan has passed its maturity date and grace period, so that overdue loans are flagged for forfeiture without manual tracking | TBD | TBD |  | Pending
22 | Sprint 5 | 22 | Loan and Transaction Management | Lost Ticket Alternate Verification | As a Cashier, I want an alternate verification process for a customer who lost their pawn ticket, so that they aren't blocked from paying or redeeming | TBD | TBD |  | Pending
Sprint 6 - Inventory & Collateral Tracking
23 | Sprint 6 | 23 | Inventory and Collateral Tracking | Register Pawned Item in Inventory | As an Operator, I want newly pawned items automatically registered into inventory with a vault location, so that the vault reflects system records | TBD | TBD |  | Pending
24 | Sprint 6 | 24 | Inventory and Collateral Tracking | Update Item Status | As an Operator, I want item status updated automatically as loans progress, so that inventory always reflects the current state of each item | TBD | TBD |  | Pending
25 | Sprint 6 | 25 | Inventory and Collateral Tracking | Perform Physical Inventory Audit | As an Admin, I want to reconcile the physical vault count against system inventory records, so that discrepancies are caught early | TBD | TBD |  | Pending
26 | Sprint 6 | 26 | Inventory and Collateral Tracking | Prepare Forfeited Items for Auction | As an Operator, I want to batch forfeited items together for auction preparation, so that unredeemed collateral can be efficiently liquidated | TBD | TBD |  | Pending
Sprint 7- Financial and Accounting
27 | Sprint 7 | 27 | Financial and Accounting | Record Cash Flow Transaction | As the System, I want to automatically record cash flow entries when a loan, payment, or forfeiture occurs, so that the ledger is always current | TBD | TBD |  | Pending
28 | Sprint 7 | 28 | Financial and Accounting | Track Daily Cash Position | As the System, I want to update the daily cash position automatically, so that Admin always sees an accurate running balance | TBD | TBD |  | Pending
29 | Sprint 7 | 29 | Financial and Accounting | Record Operating Expenses & Revenue | As an Operator, I want to record non-loan operating expenses and revenue, so that the financial picture is complete | TBD | TBD |  | Pending
30 | Sprint 7 | 30 | Financial and Accounting | Generate Financial Ledger Entries | As the System, I want to generate formal financial ledger entries, so that the pawnshop has a proper accounting record | TBD | TBD |  | Pending
Sprint 8 - Compliance and Security
31 | Sprint 8 | 31 | Compliance and Security | Log System Transaction (Audit Trail) | As the System, I want to log every create, update, and delete action across all modules, so that a complete audit trail exists without manual logging | TBD | TBD |  | Pending
32 | Sprint 8 | 32 | Compliance and Security | Flag & Review Suspicious Activity | As an Admin, I want to review system-flagged suspicious activity and decide whether to dismiss, investigate, or blacklist the customer, so that the pawnshop stays AML-compliant | TBD | TBD |  | Pending
33 | Sprint 8 | 33 | Compliance and Security | Send Due-Date Reminder Notification | As the System, I want to send due-date reminders to customers before loan maturity, so that redemption/extension rates improve and defaults are reduced | TBD | TBD |  | Pending
Sprint 9 - Reporting and Management Insights
34 | Sprint 9 | 34 | Reporting and Management Insights | Generate Outstanding Loans Report | As an Admin, I want to generate an Outstanding Loans report, so that I can monitor all currently active loans | TBD | TBD |  | Pending
35 | Sprint 9 | 35 | Reporting and Management Insights | Generate Overdue Loans Report | As an Admin, I want to generate an Overdue Loans report, so that I can follow up on loans past their due date | TBD | TBD |  | Pending
36 | Sprint 9 | 36 | Reporting and Management Insights | Generate Inventory Aging Report | As an Admin, I want to generate an Inventory Aging report, so that I can see how long items have sat in the vault | TBD | TBD |  | Pending
37 | Sprint 9 | 37 | Reporting and Management Insights | Generate Financial Summary | As an Admin, I want to generate a Financial Summary report, so that I can review revenue and expenses at a glance | TBD | TBD |  | Pending
38 | Sprint 9 | 38 | Reporting and Management Insights | Generate Compliance/AML Report | As an Admin, I want to generate a Compliance/AML report, so that I can share it with regulators or auditors | TBD | TBD |  | Pending
39 | Sprint 9 | 39 | Reporting and Management Insights | View Trends & Analytics Dashboard | As an Admin, I want to view a trends and analytics dashboard, so that I can spot patterns without manually reading raw reports | TBD | TBD |  | Pending
40 | Sprint 9 | 40 | Reporting and Management Insights | Export or Print Reports | As an Admin, I want to export or print any report, so that I can share physical or digital copies with stakeholders | TBD | TBD |  | Pending
Sprint 10 - Inventory & Collateral Tracking
41 | Sprint 10 | - | Cross-Module | User Acceptance Testing (UAT) | As the project team, we want CTM Pawnshop owner/staff to test the full system, so that it is validated against real business needs before go-live | TBD | TBD |  | Pending
42 | Sprint 10 | - | Cross-Module | Final Bug Fixing | As the project team, we want to resolve all issues found during UAT, so that the system is stable for production use | TBD | TBD |  | Pending
43 | Sprint 10 | - | Cross-Module | Backup & Restore Setup | As an Admin, I want scheduled backups configured, so that data isn't permanently lost if the local system fails | TBD | TBD |  | Pending
44 | Sprint 10 | - | Cross-Module | Production Deployment | As the project team, we want to deploy the system to CTM Pawnshop's desktop(s), so that the business can start using it | TBD | TBD |  | Pending
45 | Sprint 10 | - | Cross-Module | User Manual & Training | As a new system user, I want a user manual and basic training, so that I can operate the system without developer assistance | TBD | TBD |  | Pending
46 | Sprint 10 | - | Cross-Module | Final Documentation Handoff | As the project team, we want to hand off complete technical documentation, so that the system can be maintained or extended in the future | TBD | TBD |  | Pending
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89